## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
V/Line did not complete any gender impact assessments during the reporting period.
Following staff departures, the requirement to complete GIAs had been overlooked. A new Diversity, Inclusion and Wellness team was established in July 2023 and recruitment of key team members was completed in September 2023. Since that time, the team has:
directly engaged and raised awareness with key teams impacted by GIA obligations to educate them on their obligations to undertake GIAs as part of business-as-usual workflows
developed resources to assist impacted teams – i.e. those that are involved in developing policies, programs and services that impact the public – to conduct GIAs. These include:
  a Frequently Asked Questions (FAQ) document that addresses some common questions about GIAs at V/Line.
  an online Gender Impact Assessment Template that supports people to determine whether a GIA is required for their initiative, and guide them through the key steps to conduct a best practice assessment where it is required.
We are also in the process of developing a short, just-in-time eLearning module that helps to deepen knowledge and understanding about why GIAs are important, and guide employees on the 'how to' of conducting a GIA.
Updated our intranet to provide a central hub for employees to access relevant information, resources and tools related to GIAs.
Sent out a communication to all leaders at V/Line about their obligations to conduct GIAs and where to find information and support.
Worked directly with employees to support them to determine whether a GIA is required for initiatives and projects they are leading, and guided them to complete a GIA where it was required.
V/Line is confident that, with the above measures in place, GIAs will become part of business-as-usual workflows for programs, policies and services that directly and significantly impact the Victorian public moving forward.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Introduce gender composition targets across all functional areas to increase gender composition. Measure: Functional area gender composition analysis at least every 12 months | Ongoing | An Establishment Report and Vacancy Report analysis was undertaken in February 2023 to understand and analyse gender composition across V/Line's eight functional areas, as well as V/Line overall. This analysis helped us identify the areas of the business where gender equality improvement opportunities existed. Unsurprisingly, these were with the traditionally male-dominated areas of Operations and Network Development, Assets and Maintenance (NDAM) where the organisation continues to address physical and attitudinal barriers to achieving increased gender diversity. V/Line is due to conduct another functional area gender composition analysis in February 2024 and will continue to build on our work to identify and address barriers to achieving gender composition improvements.
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Introduce gender composition targets across all functional areas to increase gender composition. Measure: Increase women in senior leadership to 50% overall by Jun 2025 | Ongoing | In 2021, women made up 36% of senior leadership. In 2023, women in leadership increased to 42.86%, indicating an increase of over 6%. V/Line established mentorship and development programs to support professional growth and provide guidance for career advancement: V/Line mentoring program in 2023 had 40% female and 60% male uptake. It is encouraging to note that professional development requests received in the current year was highest amongst females with 61% compared to 23% males.
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Introduce gender composition targets across all functional areas to increase gender composition. Measure: Average V/Line gender composition target to 40% (may require intervention, including special measures recruitment) by Jun 2025 | Ongoing | The average gender composition for V/Line overall for the reporting period was 27% women (this figure does not included terminated employees). This represents an increase of 3% since the 2021 workplace gender audit. The Establishment Report and Vacancy Report conducted in February 2023 indicated that introducing gender composition targets across all functions equally would not be practical or achievable within the timeframes of our current GEAP, given current figures. The areas with the greatest gap are our Network Development, Assets and Maintenance (NDAM) Group where percentage of women is 15%, and Operations, where women made up 26% of the workforce in this Group. V/Line will continue to evolve our strategies and measures to address imbalances in functional groups, recognising that there is significant work we need to do to address and improve structural barriers to change before we can attract and retain women and gender diverse people in these traditionally male work spaces. These include inadequate facilities (e.g. toilets and showers) for frontline workers and inflexible working conditions which make it difficult for many women to work in the public transport sector, particularly in roles traditionally dominated by men. V/Line is working in as part of the Department of Transport and Planning Women in Transport Strategy to address structural and cultural barriers faced by women and gender diverse people in the transport sector. An example of a project that is underway is the Gender-Responsive Transport Facilities project. This project aims to develop principles for toilet and change room facilities to ensure women and gender diverse frontline workers, both on and off the route, have adequate access to safe and clean facilities during their shifts. Implementing these critical improvements to physical spaces then enables more meaningful education and awareness campaigns amongst employees in these groups to ensure we are building a safe and inclusive workplace culture for all employees.
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Design and deploy a talent attraction campaign for women Measure: Talent attraction campaigns established to support gender composition targets | Complete | Talent attraction campaigns have been established to support gender composition targets. - We conducted Female Train Driver talent attractions campaigns, which ceased in 2021, and have held a steady 25 – 26% female hire rate over the past 2 year for Driver Recruitment. Our seen the proportion of female drivers increase year on year, as follows: EOFY 2021 - 65 female drivers (12% of total driver population) EOFY 2022 - 75 female drivers (14% of total driver population) EOFY 2023 - 81 female drivers (15% of total driver population) - The first female only night shift Way Maintainer group recruitment campaign brought on 7 females in 2021. Our total number of female Way Maintainers currently sits at 13% of total Way Maintainer population (5 females). This is an increase of 10% from EOFY 2021, where we had only 1 female Way Maintainer in our workforce. - The first female Shunter commenced in 2021 and we conducted a specialist recruitment campaign to employ 7 female shunters. At EOFY 23, we had 8 female shunters employed at V/Line, which represents 15% of the total Shunter population. While we have ceased targeted female-only recruitment campaigns, our recruitment practices are such that we aim to prioritise and progress as many female driver applicants as possible through our selection process. Unfortunately, we do not see the same volume of female versus male applicants - typically we see approximately 18% female applicants versus 82% male. A very small number choose ‘other’ as gender. Given this, we do see a higher rate of application to hire conversion rates for females applying to be Drivers at V/Line. Additionally, we use a gender decoder in all our job advertisements to ensure content is gender neutral and aim to shortlist 50% female applicants where possible.
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Address unconscious bias across the full employee lifecycle Measure: Unconscious bias training offered to all managers and selection panel members | In progress | All hiring managers and people leaders are required to complete the SBS Inclusion program as part of mandatory training for leaders. This program includes the Core Inclusion module, which covers content relating to unconscious bias and strategies to reduce the impact of unconscious bias. By EOFY 2023, 213 leaders at V/Line had completed this module. In April 2023, V/Line's Talent Acquisition team completed Disability Confident Recruiters Training which was designed and delivered by the Australian Network on Disability. While the focus was on people with disability, this session also covered key principles of inclusive recruitment and hiring practices that supports V/Line strategic outcome of increasing female representation at V/Line and built intersectional knowledge around women and gender diverse people with disability.
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Normalise flexible work arrangements for all genders Measure: Gender diverse selection panel | Complete | V/Line made improvements to our Recruitment and Selection Procedure to ensure gender diversity on selection panels by specifying: - At least one member of the panel must be trained in the principles of merit and equity, and there must be a gender balance (where possible) and an independent panel member. - The hiring manager must make all reasonable efforts to achieve gender representation on selection panels. If this cannot be achieved, the selection panel report should include detail as to why it was not possible in the circumstances. This change to procedure has worked to ensure equitable outcomes for female applicants at V/Line.
Strategy: Increase the number of women in V/Line with a focus on functional areas and roles overrepresented by men. Action: Normalise flexible work arrangements for all genders Measure: Flexible Working Policy communication | Complete | As part of our commitment to supporting diverse, inclusive and equitable workplaces for all employees, V/Line undertook a review of our Flexible Work Policy to ensure that it addressed the needs of all genders in March 2023. As a result of this review, the following changes were made to the Policy: - adapted the language to better suit our Hybrid Working Procedure - simplified and updated the application process A multi-mode communications campaign was rolled out across V/Line during March and April 2023 to inform all employees about the amendments to the Policy. This included leader briefings and accompanying Discussion Guide for Managers, iAlert email notification to all employees, intranet updates and FAQs and other resources.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Identify and manage risk of work-related violence Measure: Work-related violence, risk, and hostile work environment assessment | In progress | Our People Matter 2023 survey data indicated that 19% of survey respondents experienced violence and aggression at work during the last 12 months. Of the employees who experienced violence and aggression at work: - 19% were women - 39% were non-binary or use a different term - 17% were men - 25% preferred not to share their gender Abusive language was the most common type of aggression or violence that employees experienced, irrespective of gender. A member of the public was the most common perpetrator of the violence or aggression, irrespective of gender. This data suggests that violence or aggression experienced at work may be due to working in the public transport sector rather than being gender-related.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Identify and manage risk of work-related violence Measure: Incident de-escalation, early intervention training | Ongoing | V/Line delivers a Certificate III in Rail Customer Service for frontline line customer staff. This training is Heavily contextualised for V/Line and is aligned to our policies and procedures and provides staff with the fundamental skills to perform their role. TLIG3003 Apply Positive Behaviours in the Workplace, talks about the acceptable and non acceptable behaviours in the workplace such as bullying , harassment and discrimination. We also discuss conflict between colleagues, what it looks like, the symptoms and how to deal with it such as communication styles and how and where to report ongoing and unwanted behaviour. The V/Line values and customer charter and human rights are also part of the unit. SITXCOM010 Manage Conflict and TLIO3012 Disruptive behaviours is delivered by an external provider and details how to recognise conflict, disruptive and aggressive behaviours and provides skills and techniques to manage these incidents in field. Topics include, why do people become aggressive, what emotions and behaviours to look for, what body language to be wary of and what language should be used to deescalate. The aim of this course is to provide staff with the skills to recognise situations that may became a safety risk. Included within this training is our “walk and report” work instruction, that directs customer staff to remove themselves from unsafe situations, when recognising aggressive behaviours from their training. Mental Health 1st aid is completed within this training package as is a couple of SBS units on P100. V/Line also delivers a Coping with Trauma training program for all frontline workers as part of their onboarding and induction training to ensure they are equipped and how to deal with critical incidents that include work-related violence including simple coping skills to help them deal with their experience and where to seek support from others in V/Line. V/Line's Providing Support After Trauma training course teaches our people practical skills for providing support to someone who has experienced or witnessed a potentially traumatic event. In addition the course provides awareness and skills to manage own mental wellbeing through the supportive process.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Address unacceptable behaviour, negative gendered attitudes, norms, practices, and stereotypes Measure: All staff complete mandatory training on compliance and code of conduct | Complete | V/Line adopted the Victorian Public Sector Commission (VPSC) Code of Conduct in November 2021. To facilitate awareness and education, a new How We Work at V/Line program was rolled out across the organisation in April 2022. This program part of the mandatory corporate training suite for all employees and is integrated into our new starter induction program. It includes a written guide and an eLearning module. The module aims to clarify expectations of behaviour for V/Line employees and provide guidance around concerns or instances of a breach of values, policies and/or processes. Our new starter onboarding program also covers Appropriate Workplace Behaviours workshop, which is an instructor-led session that ensures negative behaviours are adequately defined, addressed and positive behaviour is promoted. In in April 2023, V/Line launched Preventing Sexual Harassment at V/Line training as a mandatory corporate program for all existing and new employees. By EOFY 2023, 1,315 employees had completed this training. V/Line's Capability team have established governance and reporting processes to ensure that V/Line employees complete all mandatory training programs required for their role.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Prevent and respond to family violence by providing a safe and supportive working environment for all employees Measure: Opt-in family violence awareness training for all staff | Ongoing | V/Line's Family or Domestic Violence Procedure outlines the support available to employees experiencing family or domestic violence. This procedure aims to to create a supportive work environment where employees are comfortable in requesting assistance for family or domestic violence related concerns, and enables employees to continue to participate in the workplace. This procedure is supported by: - Family or Domestic Violence Workplace Safety Checklist, which is used where there are concerns about the safety of an employee or other employees in the workplace in relation to family or domestic violence, in order to assist in managing identified risks. - Family or Domestic Violence Workplace Support Plan, which is used to record actions that will be taken to support an employee experiencing family or domestic violence. In November 2022, V/Line’s Gender Equality Working Group hosted a live event for all employees, to raise awareness and have a conversation about the prevention of gender-based violence. The event was themed to coincide with 16 Days of Activism, the international movement that encourages individuals and organisations around the world to call for the prevention and elimination of violence against women and girls. Facilitated by Liana Papoutsis of Liana Papoutsis & Associates, the session explored the prevalence of domestic and family violence in Australia, the ways in which gender inequality contributes to that violence, and how gender equality legislation aims to drive changes in Victoria. After the event, information was distributed to all leaders at V/Line about how to recognise, respond and support employees who may be experiencing family or domestic violence. 250 V/Line employees attended the forum and comments and feedback in the forum chat indicated positive engagement and interest. A Domestic & Family Violence Awareness webinar was delivered to the leadership team of our Operations group - the team responsible for the entirety of the service delivery supply chain at V/Line and one of our areas where we see an overrepresentation of men. Delivered by Communicorp, a national consulting firm focused on workplace mental health and wellbeing, this session covered key concepts relating to domestic and family violence and guided participants around how to approach and have conversations around specific scenarios that may be encountered in the workplace.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Prevent and respond to family violence by providing a safe and supportive working environment for all employees Measure: Family violence disclosure training for all People Business Partners to assist managers with the process | In progress | V/Line conducted a Safe and Supported at Work - Help with Family and Domestic Violence campaign in November 2022 to communicate all the support options available to V/Line employees. As part of this campaign, People Business Partners were briefed to ensure they were able to support and reinforce key messages and actions. People Business Partners have also been trained as Workplace Contact Officers, which includes training on how to respond to disclosures of family violence. The identification of a preferred supplier to deliver Family Violence Disclosure Training for all our People Business Partners so that they can support people leaders to identify and respond according to V/Line process is currently underway with rollout planned for late 2024.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Prevent and respond to family violence by providing a safe and supportive working environment for all employees Measure: Policy, process and system review | Complete | V/Line conducted a review of the following policies and processes to ensure that they were fit for purpose in December 2023: - Family or Domestic Violence Leave procedure - Family or Domestic Violence Workplace Support Plan - Family or Domestic Violence Workplace Safety Checklist Subject to changes in V/Line's new Enterprise Agreement (currently in negotiations), all documents have been determined to be up to date and fit for purpose.
Strategy: Ensure the organisational culture promotes gender equality and prevents violence, harassment, and discrimination in the workplace. Action: Ensure effective reporting and recording systems and processes are in place Measure: Policy, process and system review | Ongoing | V/Line has introduced, reviewed and improved several systems, policies and services to ensure effective reporting and recording systems and processes support a culture that promotes gender equality and prevents violence, harassment, and discrimination in the workplace. This includes: - the launch of a dedicated Speak-Up Service in January 2023. This service is managed by Stopline, a company independent of V/Line, and enables employees, vendors and contractors to make reports about misconduct, safety breaches, or illegal, unethical or corrupt behaviour by a V/Line employee, or any behaviour that is not in the best interest of V/Line. Since it's launch, the Speak-Up service has received and investigated 51 reports from employees. - In addition to our dedicated Speak-Up Service, V/Line’s Integrity team (part of our People and Integrity group) is another channel used by our employees to raise concerns, including issues relating to discrimination. Our Integrity team received 73 queries directly from employees during the reporting period. - A review of our Sexual Harassment Policy and our Managing Performance, Behaviour and Conduct Policy in May 2022 to ensure they are fit for purpose, align with our values and support our desired culture. - Training our People Business Partners to act as Workplace Contact Officers to act as an impartial but supportive first point of contact for someone who thinks they may be experiencing discrimination, sexual harassment, vilification or victimisation at work. V/Line has also commenced work to upgrade our Human Resources Information System (HRIS) to ensure that we are better able to capture and report on the diversity of our workforce, however this is not due to be implemented until 2026 due to budgetary constraints.
Strategy: Increase the accountability of managers to role model attitudes and behaviour reflective of gender equality Action: Address negative gendered attitudes, norms, stereotypes, and unconscious bias Measure: Management training and Awareness campaigns | Ongoing | The SBS Inclusion program is mandatory training for all leaders. This program includes a Gender Equity module, which aims to improve learners' knowledge of the dynamics of gender equality, the importance and possibilities of gender equality, and tools for individuals to assess individual contributions to gender equality in the workplace. By EOFY 2023, 188 leaders at V/Line had completed this module.
Strategy: Increase the accountability of managers to role model attitudes and behaviour reflective of gender equality Action: All managers to consistently demonstrate a commitment to gender equality and preventing violence against women Measure: Gender equality KPI for Managers | In progress | All executive, directors and leaders have a Key Performance Indicator (KPI) to actively promote inclusion and diversity. Measures of success for this performance objective include the executive sponsorship of V/Line's diversity and inclusion priority cohorts (Gender, LGBTIQA+, CALD, Disability, First Nations, Generational Diversity) and increased representation of V/Line priority cohorts. All V/Line priority diversity working groups are actively sponsored by one of our executive directors, who work with the group to: - Ensure alignment of Working Group direction with overall business strategy. - Promote and champion the work of the group to enable progress. - Act as a representative of the Working Group at the Executive Management Committee and with other senior leaders. - Support the Working Group to build connections and influence stakeholders. - Ensure the Working Group have the resources they need to be successful.
Strategy: Increase the accountability of managers to role model attitudes and behaviour reflective of gender equality Action: All managers to consistently demonstrate a commitment to gender equality and preventing violence against women Measure: Improvement in People Matter Survey results | In progress | All executive, directors and leaders have a Key Performance Indicator (KPI) to foster a workplace culture that promotes positive physical and mental health and wellbeing at work. Measures of success for this performance objective include taking action on annual People Matter Survey feedback relevant to their group and/or team through the development and execution of an action plan, and to address any inappropriate behaviours if/when they arise.
Strategy: Implement evidence-based approaches to close the gender pay gap Action: Understand pay gaps at all levels with the view to reducing these gaps Measure: Undertake further review of the gender pay gap and then determine evidence-based approaches to close the gap | In progress | A gender pay gap analysis was undertaken at V/Line at EOFY 23 and indicated: - Across V/Line’s full workforce irrespective of employment basis and classification, women were paid on average 10.4% less base salary than men. This is a 1.2% decrease since the 2021 audit. - The gap widened when considering total salary, with women at V/Line paid 15% less on average than men. - the gender pay gap decreased for women in leadership roles (Executive and Senior Leadership teams) with a pay gap of 9.7% (base salary). V/Line has established a Remuneration Committee which sits bi-monthly and is responsible for ensuring fair and equitable pay across all areas of V/Line, and who are responsible for considering gender pay gap analysis data and determining remedial action required. In the second quarter of 2023, V/Line engaged Ernst and Young (EY) to conduct an Investigation on Overtime Claims. Overtime has a significant impact where data shows that this increases the pay gap significantly. The commissioning of this investigation substantiated V/Lines initial findings and steps are being implemented to obtain additional insights and manage this risk.
Strategy: Implement evidence-based approaches to close the gender pay gap Action: Understand pay gaps at all levels with the view to reducing these gaps Measure: At least one evidence-based strategy in place and progressing to close the gender pay gap | In progress | Recognising the significant impact of overtime on pay gap, the feasibility of implementing a Time and Attendance module is to be progressed through three inflight connected projects: Human Resources Information System (HRIS), Payroll Improvement Project (PIP) and HASTUS Workforce Management, with consideration of scoping to address red flags and limitations outlined in the EY Investigation.
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Responsibility for implementation of the strategies and measures of our GEAP sits with V/Line's People and Integrity, and driven by our Diversity, Inclusion and Wellness team, who collaborate with other members of the team to deliver on our GEAP commitments. Key people in the team accountable for the work are our Director of Diversity, Inclusion and Wellness and Head of Organisational Culture, Capability and Diversity. Both roles are full time roles dedicated to delivering on the organisation's diversity and inclusion portfolio of work, supported by members in our Workforce Systems, Talent Acquisition and People Services teams as required. V/Line has also established a Gender Equality Working Group made up of employees and members of the Diversity, Inclusion and Wellness team, and supported by an executive sponsor to monitor V/Line’s adherence to the Gender Equality Act 2020. It provides oversight and support around the development and management of key initiatives that support GEAP strategies and measures to ensure V/Line’s continued adherence to the Act.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Like many organisations in the transport sector, gender composition is heavily over-represented by men, particularly in our Operations and Network Assets and Maintenance functional groups. Nevertheless, we did see progress in gender composition of the organisation, with a 3% increase in the number of women in the organisation from the 2021 workplace gender audit to 27% of our overall workforce. Our workforce system was not appropriately established to collect data on non-binary or gender diverse employees and as such we were not able to report on this in our 2021 audit. While we are still in the process of sourcing a new HRIS to be implemented in the coming years to enable better data gathering and reporting, we made changes to our system as well as our new employee forms to enable us to capture this data in the interim. As a result, our 2023 audit captured 1 self-described employee in our 2023 audit, up from 0 in 2021, a small but encouraging sign of progress. 2021 gender composition - Women=24%, Men 76% Self-described=0% 2023 gender composition - Women=27%, Men 73% Self-described=0.4%
Gender composition of governing bodies | Yes | In 2021, women made up 33% of the V/Line board, while men made up the remaining 67%. Pleasingly, representation of women increased to 50% of the board in our 2023 audit, thus achieving gender parity between men and women in our governing body. 2021: Women= 33%, Men=67%, Self-described=0 2023: Women=50%, Men=50%, Self-described=0
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Assessing equal remuneration for work of equal or comparable value across all levels of the workforce irrespective of gender based on level to the CEO does not necessarily provide evidence of comparable value due to the wide variation of roles within each level. Nevertheless, when we compare the gender pay gap of mean base salary from 2021 to 2023, we can see that there has been a positive trend to our reporting in this area, with a reduction of 1.2% overall. We do see a pay gap of 36.9% for self-described genders, however this accounts for one employee and is therefore an unreliable indicator of actual pay gap at this point in time. 2021 Mean Base: 11.6% gender pay gap 2023 Mean Base: 10.4% gender pay gap
Sexual harassment in the workplace | No | In our 2021 audit, 3 formal complaints of sexual harassment were received and women made up 100% of complainants. Our 2023 audit results see an increase in the number of sexual harassment complaints received to 8 overall - women made up 88% of complainants (representing 7 women), while men made up 12% (1 man). All complaints received were handled internally by the People and Integrity team at V/Line. At face value, these numbers may represent a regression in this indicator area. Given the significant efforts that have been made to raise awareness and further educate our people to ensure a workplace free of sexual harassment, this increase in formal complaints may in fact be a favourable indicator that more people are recognising the behaviour and feeling better supported to speak up and take action against experiences of sexual harassment. Nonetheless, when looking at our 2023 People Matter survey data, we see 102 employees experienced sexual harassment at work in the 12 months before the survey, which is significantly more than the 8 people who submitted a formal complaint. Both women and men who experienced sexual harassment reported the same primary reasons for not submitting a formal complaint: - 49% of women and 43% of men believed there would be negative consequences for their reputation (e.g. they would be blamed or not believed or thought to be overreacting) - 46% of women and 35% of men didn't think it would make a difference - 34% of women and 24% of men didn't think it was serious enough. Of those who preferred not share their gender, 47% didn't think it would make a difference and/or that they believed there would be negative consequences for their reputation (e.g. they would be blamed or not believed or thought to be overreacting). We are unable to report on reasons that self-described employees did not submit a formal complaint due to reporting thresholds that protect anonymity. The consistency in reasons given for not submitting a formal complaint indicates that we still have significant work to do to build employee confidence in our reporting processes and procedures as we progress our gender equality work. 2021: Women=100%(3) 2023: Women= 88%(7), Men=12%(1)
Recruitment and promotion practices in the workplace | No | Rates of employee movement relating to recruitment, promotion and departures between the 2021 workplace audit and the 2023 audit indicate a shift in favour of men. When comparing audit data for recruitment overall, V/Line's recruitment of women has declined from 47% in 2021 to 34% in 2023, representing a decline of 13% across the audit periods. An increase in the men recruited for the same periods accounts for 12% of this difference, while the remaining 1% is accounted for by employees who self-describe their gender, which is a small but positive sign of progress to acknowledge. Departure figures for women across the two audits have increased, with women making up 34% of exits in the 2023 audit compared to 27% of exits in 2021. In comparison, 67% of men departed the organisation in the 2023 audit, a 6% decrease from the 73% total in 2021. This trend continues to be reflected in permanent promotions over the two audit periods where we see women drop from 33% of permanent promotions in 2021 to 31% in 2023. This 2% difference is reflected in an increase of men who received permanent promotions increasing from 67% in 2021 to 69% in 2023. We do, however, see positive movements with regards to internal secondments where women have increased from 30% of secondment appointments in 2021 to 42% in 2023. Women also make up 42% of employees taking up career development, training and mentoring opportunities, which is a significant proportion when we consider they make up only 27% of overall gender composition at V/Line. As an example, 50% (5/10) of our graduate pool in 2023 were female, 3 of whom have now secured senior roles at V/Line. This indicates there is a keen interest and appetite for promotion, leadership and career progression from women at V/Line and emphasises the need for the organisation to continue to enhance our policies and practices to ensure career advancement for women and gender-diverse employees. 2021 People recruited: Women=47%, Men=53%, Self Described=0 2021 People exited: Women=27%, Men=73%, Self Described=0 2021 Permanent Promotions: Women=33%, Men=67%, Self Described=0 2021Career Development: Data Unavailable 2021 Higher Duties: Women=43%, Men=57%, Self Described=0 2021 Internal Secondments: Women=30%, Men=70%, Self Described=0 2023 People recruited: Women=34%, Men=65%, Self Described=1% 2023 People exited: Women=34%, Men=67%, Self Described=0 2023 Permanent Promotions: Women=31%, Men=69%, Self Described=0 2023 Career Development: Women=42%, Men=57%, Self Described=1% 2023 Higher Duties: Data Unavailable 2023 Internal Secondments: Women=42%, Men=58%, Self Described=0
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Data relating to availability and utilisation of terms, conditions and practices relating to parental, family violence and carers leave was not available when the workplace gender audit was conducted in 2021. While we do not have a baseline to measure shifts in uptake of these leave entitlements, we consider our ability to report on this data in the 2023 audit represents progress. Our 2023 audit data indicates that we have ongoing work to do normalise and encourage the take up of flexible work options for all our senior leaders but in particular male leaders to provide role models as a way of attracting and retaining employees across all age groups and genders. Of the carers leave taken for the 2023 audit, 26% was taken by women (413 employees) and 74% by men (1202 employees). Based on the composition of our workforce, this indicates that men and women take carers leave evenly at V/Line. 2021: Data Unavailable 2023 Senior Leader flexible work - Women=3, Men=0, Self-described=0 2023 Parental leave exits= Women=0, Men=0, Self-described=0 2023 Family violence leave: Women=3, Men=1, Self-described=0 2023 Carers leave: Women= 413 (26%), Men= 1202 (74%), Self-described=0
Gendered segregation within the workplace | Yes | V/Line saw an increase in the number of women across all occupational categories, except for those in the Professional category, where the number remained unchanged at 40% of the total workforce in this category. Of significance for V/Line are the increases we saw in the occupations that have been historically male-dominated or male-only positions: - a 3% increase in the Labourers category, bringing women up to 7% overall - a 5% increase in the Technicians and Trade workers category, so that women now make up 15% of workers in this category - a 2% increase in the Machinery Operators category, where women have gone from 11% to 13% of workers in this category While modest, these increases demonstrate positive shifts in building gender diversity in occupations that are overrepresented by men. We also saw a 5% increase of women in the Managers category, bringing women to 34% of workers in this category and a 4% increase of women in the Sales Workers category. This latter data point is significant because all positions in the Sales Workers category at V/Line are in our Operations functional group, where women made up 26% of the workforce in this group for the 2023 audit period. 2021 Managers: Women=29% 2023 Managers: Women=34% - INCREASE 5% 2021 Labourers: Women=4% 2023 Labourers: Women=7% - - INCREASE 3% 2021 Technicians and Trade workers: Women=10% 2023 Technicians and Trade workers: Women=15% - INCREASE 5% 2021 Clerical and Administrative Workers: Women=43% 2023 Clerical and Administrative Workers: Women=46% INCREASE 3% 2021 Machinery Operators: Women=11% 2023 Machinery Operators: Women=13% - INCREASE 2% 2021 Professionals: Women=40% 2023 Professionals: Women=40% - UNCHANGED 2021 Sales Workers: Women=30% 2023 Sales Workers: Women=34% INCREASE 4% (all Sales Workers positions are in Operations)

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled